## Sheet1
034371 Project in design for manufacturing — Spring semester 2024
Gantt chart
| March 2024 |  |  |  | April 2024 |  |  | May 2024 | [6 empty] | June 2024
| 4-8 | 11-15 | 18-22 | 25-29 | 1-3 | 8-12 | 15-19 |  | 6-10 | 13-17 | 20-24 | 25-26 | 27-29 | 30- June 1 | 3-7 | 11-14 | 17-19
Group forming
Object selection
System requirements review (SRR)
Technical specification
Concept design
Preliminary design review (PDR)
Robot Arm Design + modeling
Tower Design
Basement + Assembling
blades
box (shaft, bearing, housing, lid, screw)
FEM
Arm (wielding)
guide rail
Power screw + Motor
elevator(standard part+mounting)
turn table
Detailed design: Tolerancing
Detailed design: Manufaturing
Group presentation before all groups
Critical design review (CDR)